# Project Mariner Completion Checklist

Sale of the Seabrook Quay Hotel business and assets

Working version 7 | 27 May 2026 | Proposed completion 2 June 2026
Prepared for Northpoint Hospitality Limited | Client internal copy

SLL  Seabrook Leisure Limited (seller)    NPH  Northpoint Hospitality Limited (buyer)
WL  Wrenfield Legal LLP (buyer solicitors)    BP  Bellport Partners (seller solicitors)

Fictional specimen for house-style reference only. Matter-specific entries are not a precedent list of required deliverables.

| Ref | Document or action | Responsibility | Timing | Source | Status | Internal notes |
| --- | --- | --- | --- | --- | --- | --- |
| A Before signing |  |  |  |  |  |  |
| A.1 | Agree the scope of the hotel assets and excluded equipment | Both parties | Before exchange | APA sch 1 | Complete | Keep the Seller's antique launch outside the sale perimeter. |
| A.2 | Confirm client authority for the £175,000 price retention | NPH / WL | Before exchange | Client instruction | Complete | Client will not increase the retention without investment committee approval. |
| B Signing |  |  |  |  |  |  |
| B.1 | Execute and exchange the asset purchase agreement | SLL / NPH | On exchange | APA cl 3.1 | Complete | Exchanged at 16:20 on 14 May 2026. |
| B.2 | Pay the contractual deposit to the stakeholder | NPH | On exchange | APA cl 3.2 | Complete | Deposit receipt held on Mariner finance file. |
| B.3 | Deliver the disclosure letter and receipt acknowledgement | SLL / NPH | On exchange | APA cl 3.3 | Complete | Seller resisted disclosure of the service lift report; now attached. |
| C Before completion |  |  |  |  |  |  |
| C.1 | Obtain the landlord's licence to assign the hotel lease | SLL / BP | Before completion | APA cl 4.1 | In progress | Landlord's counsel awaits the Northpoint parent accounts. |
| C.2 | Agree apportionments for bookings and advance room deposits | SLL / NPH | 3 Business Days before completion | APA cl 5.2 | In progress | Check the £22,400 coach-party deposit against booking ledger. |
| C.3 | Deliver the agreed employee information and consultation record | SLL | 5 Business Days before completion | APA cl 6.4 | Awaiting draft | Employment team reviewing the night-manager arrangements. |
| C.4 | Agree the catering supplier novation | SLL / NPH | Before completion | APA sch 3 | In progress | Do not accept the revised minimum-spend commitment without client approval. |
| C.5 | Confirm buyer property-insurance cover and handover contacts | NPH | Before completion | APA cl 7.2 | To confirm | Broker to confirm cover from actual handover, not proposed date. |
| D Completion |  |  |  |  |  |  |
| D.1 | Execute the lease assignment and release the licence to assign | SLL / NPH / BP | At completion | APA sch 4 para 1 | Awaiting signature | Use engrossment dated 26 May only. |
| D.2 | Pay the balance of consideration and agreed apportionments | NPH | At completion | APA cl 7.3 | Not started | Retain £175,000 under the agreed stakeholder arrangement. |
| D.3 | Deliver keys and signed inventory for the 42-bedroom hotel | SLL | After funds receipt | APA sch 4 para 3 | To confirm | Site manager to photograph meter readings and damaged kitchen panels. |
| D.4 | Release the catering novation and assign transferable bookings | SLL / NPH | At completion | APA sch 4 para 4 | Awaiting signature | Wedding booking M26-014 remains subject to the separate customer consent. |
| D.5 | Confirm completion and authorise the staff announcement | WL / BP | After release of documents | APA cl 7.5 | Not started | Do not send the announcement while licence release is outstanding. |
| E After completion |  |  |  |  |  |  |
| E.1 | Deliver the final apportionment reconciliation | SLL | 10 Business Days after completion | APA cl 8.1 | Not started | Review minibar stock separately from ordinary operating supplies. |
| E.2 | Submit the agreed lease registration application | WL | Within applicable filing period | APA cl 8.3 | To confirm | Property team to confirm the statutory timetable for this lease. |
| E.3 | Obtain the missing refrigeration maintenance records | SLL / BP | 20 calendar days after completion | APA cl 8.5 | Not started | Client has asked for the original contractor service history. |
| E.4 | Review release of the price retention | NPH / SLL | 6 months after completion | APA cl 9.2 | Not started | Release depends on the agreed roof-work evidence, not passage of time alone. |